## Sheet1
Goal: To assist SVRAs and related agencies and professionals to successfully meet the requirements of WIOA
Objective 1: Develop knowledge that will assist SVRAs and related professionals and agencies to meet effectively meet the requirements of WIOA
Activities | Milestone - Outcomes
|  | Year 3 | Year 4 | Year 5
Add to the literature review on evidence-based and promising practices in the five topic areas as they are identified and/or developed | Completed literature review | Q1-4 | Q1-4 | Q1-4
Responsible Entity and Person(s): SDSU-CC, CK, LO and FS; NDI-DK; GW-MMK and MD; UA-JM and SO; CSAVR - WDC; PW-BB
Continue to develop and refine tool kits for all five topic areas | Five curriculum guides completed with regular updates | Q1-4 | Q1-4 | Q1-4
Responsible Entity and Person(s): SDSU - Topics 2&3; NDI/LEAD Center - Topics 4&5; UA - Topics 3&4; GW - Topics 1 & 2; PW - Topics 4&5
Objective 2: Provide technical assistance and dissemination activities to SVRAs and related agencies and rehabilitation professionals related to the five topic areas to help them develop the skills and processes needed to meet the requirements of WIOA.
Continue to provide intensive TA to the 23 SVRAs with active agreements developed in the first two years and develop new ITAs and provide TA to the new VR agencies. | Thre are 21 agreemnts active representing 23 VR agencies. There are several agreements pending review and in development. | As many as needed | As many as needed | As many as needed
Responsible Entity and Person(s): SDSU - Topics 2&3; NDI/LEAD Center - Topics 4&5; UA - Topics 3&4; GW - Topics 1 & 2; PW - Topics 4&5
A broad range of targeted, specialized and universal TA is provided to SVRAs and related professionals to effectively respond to the changes required by WIOA | State-of-the art IT platform continuously populated with information to assist SVRAs in responding to WIOA. Targeted activities and events occur as needed | Q1-4 | Q1-4 | Q1-4
Responsible Entity and Person(s): SDSU- CDL
Grow the Career Index Plus pilot projects through focused training, linkages to other WINTAC projects and marketing of the benefits of usage | All SVRAs have access to the program at this time. Five intensive TA states have received focused TCI+ training. Nine other States have received targeted TA on usage. This number will conintue to expand as needed and requested throughout Year 3. | Q 1-4 | Q 1-4 | Q 1-4
Responsible Entity and Person(s): Career Index - KDN and Portals LLC
Conitnue the SARA pilot project in Kentucky, Nevada and Alaska | SARA fully operational in all three SVRAs | Q1-4 | Q1-4 | Q1-4
Responsible Entity and Person(s): Career Index - KDN
Implement the peer mentoring pilot project in identified SVRAs | Peer mentoring established in multiple sites, including Florida and Alaska. There are three other State sin discussion and planning at this time, with the possibility of conitnuoius expansion throughout the project. | Q1-4 | Q1-4 | Q1-4
Responsible Entity and Person(s): Policy Works - BB
Conduct the customized employment training pilot projects in selected States in partnership with the Y-TAC | There are seven VR agencies that are currently a part of the pilot project, which includes training in ten sites throughout those states. There are at least three other States (New Hampshire, DC, and Arizona) that will be added within the next few months). Additional sites will be added base don request, capacity and available funding. | Q1-4 | Q1-4 | Q1-4
Responsible Entity and Person(s): SDSU - CK; Y-TAC - Curtis Richards
Develop a customized employment national certificate that will be available to SVRAs and CRPs to develop capacity, ensure consistency and fidelity of service delivery, and increase the quantity and quality of employment outcomes for individuals with the most significant disabilities | A national certificate is developed and made available to SVRAs and CRPs | Q1-4 | Q1-4 | Q1-4
Responsible Entity and Person(s): SDSU - CK
Develop online/electronic resources to provide to SVRAs that will help them deliver the five required pre-employment transition services | Fully developed online/electronic resources that are available on the WINTAC website. These are nearing completion and will be posted on the website. | Q1-4 | Q1-4 | Q1-4
Responsible Entity and Person(s): GW - MK, MD and CJ
Objective 3: Coordinate activities between SVRAs and their partners to assist in their effective response to the requirements of WIOA.
Establish CoPs in each of the five topic areas that act as vehicles for communication and exchange of information | CoPs established and functioning. These are established and funcitoning and will conitnue to be developed throughout Year 3. | Q 1-4 | Q 1-4 | Q 1-4
Responsible Entity and Person(s): SDSU - Topics 2&3; NDI/LEAD Center - Topics 4&5; UA - Topics 3&4; GW - Topics 1 & 2; PW - Topics 4&5
Communicate, coordinate and collaborate with other DOE, DOL, DOC, HHS funded projects to support learning and KD and KT. | Number of related TACs and other projects contacted and engaged. As of the end of Year 2, we have formally partnered 2o times in intensive TA agreements with other TA Centers. We partner in CoPs, targeted TA and numerous other joint activities at conferences and events. | Q 1-4 | Q 1-4 | Q 1-4
Responsible Entity and Person(s): Project Directors from each partner
Maintain ongoing communication with RSA project officer and other RSA staff as required | Frequency of communication and number of staff from RSA engaged | Q 1-4 | Q 1-4 | Q 1-4
Responsible Entity and Person(s): Project Directors from each partner