## Sheet1
Goal: To assist SVRAs and related agencies and professionals to successfully meet the requirements of WIOA
Objective 1: Develop knowledge that will assist SVRAs and related professionals and agencies to effectively meet the requirements of WIOA
Activities | Milestone - Outcomes
|  | Year 4 | Year 5
Keep the topic area tool kits up to date on evidence-based and promising practices and resources as they are identified and/or developed | Up-to-date tool kits for all areas | Q1-4 | Q1-4
Responsible Entity and Person(s): SDSU-CC, CK, SO and FS; NDI-DK, RA, BH, NP and LA; GW-MMK, MD, BS, CJ; CSAVR - JC and RV; ICI - JC and CG; UW-LF and KM
Incorporate the Tool Kits from Explore-VR to the WINTAC site so that business engagement information is accessible for users from one site | Business Engagement Information is completely migrated to the WINTAC site | Q1-4 | Q1-4
Responsible Entity and Person(s): SDSU - CC, MO and YJ; ICI - JC and CG
Expand the WINTAC website to include Tool Kits for Labor Market Information, TCI+ and Apprenticeships (in addition to business engagement cited above) | Topic area expansion on the website with accompanying tool kit development | Q1-4 | Q1-4
Responsible Entity and Person(s): SDSU - CC, MO and YJ; ICI - JC and CG
Objective 2: Provide technical assistance and dissemination activities to SVRAs and related agencies and rehabilitation professionals related to the eight topic areas to help them develop the skills and processes needed to meet the requirements of WIOA.
Continue to provide intensive TA to the 34 SVRAs with active agreements developed in the first three years and develop new ITAs and provide TA to the new VR agencies. | There are 32 agreements active representing 34 VR agencies. There are eight more agreements that are either completed and awaiting signature from the VR program, or near completion. | As many as we have capacity for | As many as we have capacity for
Responsible Entity and Person(s): All teams and partners
Expand TA topic areas to include business engagement, TCI+/labor market information and apprenticeships and provide technical assistance at all levels to SVRAs that request TA and training as our capacity allows | The number of agencies receiving TA in the additional areas will be documented in the ITAs. Outreach and marketing processes will occur continuously. | Q1-4 | Q1-4
Responsible Entity and Person(s): SDSU- CDL
A broad range of targeted, specialized and universal TA is provided to SVRAs and related professionals to effectively respond to the changes required by WIOA | State-of-the art IT platform continuously populated with information to assist SVRAs in responding to WIOA. Targeted activities and events occur as needed | Q1-4 | Q1-4
Responsible Entity and Person(s): SDSU- CDL
Grow the Career Index Plus projects through focused training, linkages to other WINTAC projects and marketing of the benefits of usage | All SVRAs have access to the program at this time. Eleven intensive TA states have received focused TCI+ training. Twenty-four other States have received targeted TA on usage. This number will continue to expand as needed and requested throughout the final two years of the project. | Q 1-4 | Q 1-4
Responsible Entity and Person(s): Career Index - KDN and Portals LLC - JH
Continue the SARA pilot project in Kentucky, Nevada and Alaska | SARA fully operational in all three SVRAs | Q1-4 | Q1-4
Responsible Entity and Person(s): Career Index - KDN
Implement the peer mentoring pilot project in identified SVRAs | Peer mentoring established in multiple sites, including Florida, Alaska and Mississippi. There are three other States in discussion and planning at this time, with the possibility of continuous expansion throughout the final two years of the project. | Q1-4 | Q1-4
Responsible Entity and Person(s): Policy Works - BB
Conduct the customized employment training pilot projects in selected States in partnership with the Y-TAC and NTACT | There are eight VR agencies that are currently a part of the projects, with at least eight other States that have expressed a desire to be part of the project. Additional sites will be added based on request, capacity and available funding. | Q1-4 | Q1-4
Responsible Entity and Person(s): SDSU - CK; Y-TAC - Wendy Quarles
Develop online/electronic resources to provide to SVRAs that will help them deliver the five required pre-employment transition services | Fully developed online/electronic resources that are available on the WINTAC website. These are complete and posted on the website. Usage is being tracked and will be reported quarterly. | Q1-4 | Q1-4
Responsible Entity and Person(s): GW - MK, MD, BS, CJ & DR
Objective 3: Coordinate activities between SVRAs and their partners to assist in their effective response to the requirements of WIOA.
Establish CoPs in each of the five topic areas that act as vehicles for communication and exchange of information | CoPs established and functioning. These are established and functioning and will continue to be developed throughout Years 4 and 5. | Q 1-4 | Q 1-4
Responsible Entity and Person(s): SDSU - Topics 2&3; NDI/LEAD Center - Topics 4,5 & 8; GW - Topic 1; ICI- Topic 6; TCI & Portals - Topic 7
Communicate, coordinate and collaborate with other DOE, DOL, DOC, HHS funded projects to support learning and KD and KT. | Number of related TACs and other projects contacted and engaged. As of the end of Year 3, we have formally partnered 24 times in intensive TA agreements with other TA Centers. We partner in CoPs, targeted TA and numerous other joint activities at conferences and events. | Q 1-4 | Q 1-4
Responsible Entity and Person(s): Project Directors from each partner
Maintain ongoing communication with RSA project officer and other RSA staff as required | Frequency of communication and number of staff from RSA engaged | Q 1-4 | Q 1-4
Responsible Entity and Person(s): Project Directors from each partner